## Production Timeline
Day | Date | Item | Who owns | Time In | Time out | Confirmed? | Notes
Friday |  | Mark out Stalls |  | 6pm
|  | Site Managers in |  | 6pm
|  | Fencing In |  | 6pm
|  | On-site Electrician In |  | 6pm
|  | Trash cans |  | 6pm
|  | Security Guards in |  | 6pm
|  | Bar Infratstructure Drop Off |  | 6pm
|  | Site Lighting - Midnight |  | 6pm
|  | Overnight Security in |  | 6pm | 6am
|  | Crosswinds load-in - build VIP and FOH risers and platforms |  | 6pm
Saturday |  | Site Managers In |  | 6am
|  | Test Radio's |  | 6am
|  | Sponsors Load In |  | 6am
|  | Security Guards In |  | 6am
|  | Toilets In |  | 7am
|  | Food Vendors In |  | 7am | 8pm
|  | Décor |  | 6am
|  | GigRIg |  | 6am | 6pm
|  | Volunteer - Site Crew In |  | 10am
|  | Berryblast In |  | 6am
|  | Sound Check in |  | 11am
|  | AFD Walk Through |  | 12pm
|  | Banners up |  | 11am
|  | Lights load in at front of house |  | 11am
|  | Cleaners In |  | 11am
|  | Trash Carts in |  | 10am
|  | Site Managers In |  | 7 30am
|  | Sponsors In |  | 9am
|  | Fence line banner hangs |  | 10am
|  | Trash Roll-Off in (AR&R) |  | 10pm
|  | Production Meeting |  | 10am
|  | Main Security In |  | 11am
|  | Sponsor Actvations Live |  | 12:00
|  | Security Briefing |  | 11am
|  | Gates Open |  | 12:30pm | 10pm
|  | Water Drop Off |  | 2pm
|  | Main Security In |  | 3pm
|  | Sponsor Activations Live |  | 3pm
|  | Security Briefing |  | 3 15pm
|  | Gates Open |  | 3 30pm
|  | Cirrus Logic Party |  | 5pm
|  | Show at Long Center Starts |  | 9pm
|  | Overnight Security in |  | 9pm
|  | Curfew |  | 10 pm
|  | All Vendors / Sponsors Load-Out ( sound / lights / tents / etc) |  | 10 30pm
|  | Closure Ends |  | 0:00
|  | Gig Rig Load-out |  | 10pm
|  | Vendors Load-out |  | 8pm
|  | Security In |  | 10pm
|  | Site Managers In |  | 10pm
|  | Berryblast Out |  | 10pm
|  | All remaining vendors load-out |  | 10pm
|  | Clean up |  | Alround
|  | Security Out |  | 0:00
|  | Fencing Out |  | 0:00
|  | Cleaners Out |  | 0:00
|  | Anything else |  | 0:00